## Project Breakdown EN
No | Feature | Module | Sub-module | Function | Detail / Requirement | MVP / Phase | Priority | Owner | FE Est | BE Est | Test Est | Tools | Database Tables | API / Endpoint | Acceptance Criteria | Risk / Question | Cherry/Gary Can Help | Kien Must Handle | Status
1.1 | Foundation | Authentication | User login | Supabase Auth setup | Email/password login, forgot password, reset password, role-based login for Superintendent, Admin, Staff. Use Supabase Auth rather than custom password logic. | MVP | P0 | Kien + Cherry/Gary UI | 8 | 12 | 6 | Supabase Auth, Next.js | users, facilities | POST /auth/login; POST /auth/reset | Users can login and are redirected based on role. | RLS and role mapping must be correct before pilot. | Build login/reset UI and empty states. | Configure Supabase Auth, JWT, roles, RLS policies. | To discuss
1.2 | Foundation | Multi-tenancy | Facility isolation | facility_id and RLS | Every core table must include facility_id. Care home A must not see care home B data. | MVP | P0 | Kien | 2 | 16 | 8 | Supabase PostgreSQL, RLS | all core tables | N/A | RLS test confirms cross-facility access is blocked. | Data leakage is critical risk. | Prepare facility selector UI only. | Design RLS policies and test cases. | To discuss
2.1 | Roster | Roster Management | Calendar view | Weekly and monthly roster | Display 7-day and 28-day roster with staff rank, wing/floor, shift type, shift tasks as display labels, status, worked hours. | MVP | P0 | Cherry/Gary + Kien | 24 | 14 | 8 | Next.js, Tailwind, shadcn/ui | roster_versions, shifts, shift_assignments, staff | GET /rosters/:period | Roster page shows real DB data, not mock data. | Prototype mock data may not match DB schema. | Improve existing prototype roster UI. | Provide API and data mapping. | To discuss
2.2 | Roster | Roster Management | Create/Edit shift | Manual shift CRUD | Manager can create A/P/N/AN/AL/OFF/SLEEP shifts, edit shift time, wing, required role, and assign/unassign staff. | MVP | P0 | Kien + Cherry/Gary UI | 20 | 24 | 10 | Next.js, FastAPI/Supabase | shifts, shift_assignments | POST /shifts; PATCH /shifts/:id; DELETE /shifts/:id | Manager can create, edit, delete, assign and unassign shifts. | Manual edits must be logged for AI acceptance rate. | Build modal and forms. | Implement APIs and manual_override_log. | To discuss
2.3 | Roster | Roster Management | Save/Publish | Roster version workflow | Save draft roster, publish selected roster, lock published version, allow rollback to previous published roster. | MVP | P0 | Kien | 8 | 20 | 8 | Supabase, FastAPI | roster_versions, reports, audit_log | POST /rosters/save; POST /rosters/publish | Published roster becomes visible to staff app. | Wrong publish could affect real operations. | Build buttons and confirmation UI. | Versioning, rollback, audit log. | To discuss
2.4 | Roster | Roster A/B/C | 3-plan comparison | Generate and compare Roster A/B/C | MVP may use CP-SAT with different soft weights. Show cost, agency shifts, OT/CL dashboard, preference score, compliance status. | phsse 2-4 | P0 | Kien + Cherry/Gary UI | 20 | 32 | 12 | OR-Tools CP-SAT, FastAPI, Next.js | optimization_runs, roster_versions, roster_kpi | POST /optimize-roster | Manager can compare three roster options. | Runtime may exceed 60 seconds; need job status. | Build comparison cards/table. | 3-plan engine, objective scores, job handling. | To discuss
3.1 | Compliance | Compliance Engine | H1-H13 hard constraints | Rule mapping | Translate H1-H13 and SWD staffing ratio rules into machine-checkable constraints and violation logs. | MVP | P0 | Kien | 8 | 36 | 16 | OR-Tools CP-SAT, Supabase | compliance_rules, violation_log, shifts, shift_assignments | GET /compliance; POST /validate-roster | Hard constraint violations are listed clearly. | LLM must not be used as hard-constraint validator. | Build violation cards and warning UI. | Implement rules, tests, severity levels. | To discuss
3.2 | Compliance | Compliance Dashboard | Staff-to-resident ratio | Ratio calculation by shift/wing/role | Calculate RN/HW/CW/AW ratio by shift and wing, matching prototype Staffing Ratio card. | MVP | P0 | Kien + Cherry/Gary UI | 12 | 18 | 8 | SQL View, FastAPI, Next.js | facilities, wings, shifts, shift_assignments, staff | GET /compliance/ratio | Dashboard shows ratio and whether it meets minimum standard. | Resident count may be manually updated; need source of truth. | Build dashboard stat cards. | Implement ratio SQL/API and edge cases. | To discuss
3.3 | Compliance | AN/PH/AL Rules | AN and leave compliance | AN limit, sleeping day, rest day and PH handling | Track AN count, sleeping day, rest day, public holiday, AL balance, and warning rules. | MVP + Phase 2 | P0/P1 | Kien | 8 | 28 | 12 | CP-SAT, SQL, Python optional | leave_requests, shift_assignments, roster_kpi | GET /compliance/an; GET /leave/balance | AN over-limit and missing rest rules are detected. | AN rules are operationally complex; confirm with RN advisor. | Help define nursing rules in plain language. | Implement logic and tests. | To discuss
4.1 | Staff App | Staff Roster View | View own schedule | Staff can view own roster | Staff can view shift details, shift status, wing/floor, role, task labels, and download own schedule. | MVP | P0 | Cherry/Gary + Kien | 24 | 12 | 8 | Next.js PWA, Supabase Auth | staff, shift_assignments, shifts | GET /staff/me/roster | Staff only sees own roster. | Permission errors could expose other staff schedules. | Build mobile screens. | Auth, permission, API filters. | To discuss
4.2 | Staff App | Leave Requests | AL/day off/specific duty request | Submit and track requests | Staff can submit AL/day-off/specific duty request before roster cutoff; manager can approve/reject. | MVP | P0 | Kien + Cherry/Gary UI | 24 | 20 | 10 | Next.js PWA, Supabase | leave_requests, notifications | POST /leave-requests; PATCH /leave-requests/:id | Request lifecycle works: pending, approved, rejected. | Approval must update roster if needed. | Build forms and lists. | State transitions, APIs, audit. | To discuss
4.3 | Staff App | Urgent SL/DSL | Emergency sick leave request | Submit urgent SL/DSL and trigger replacement suggestion | Staff submits urgent sick/special leave for upcoming shift; manager receives alert; system suggests available replacement candidates. | MVP | P0 | Kien + Cherry/Gary UI | 20 | 30 | 12 | Rule engine, notification | sl_incidents, leave_requests, shift_assignments, staff | POST /sl-incidents; GET /replacement-candidates | SL incident is logged and replacement candidates are shown. | Directly affects ROI A2; data must be accurate. | Build request/approval UI. | Matching rules, alerts, ROI logging. | To discuss
4.4 | Staff App | Notification | In-app/email alerts | Shift and request notifications | Notify staff for new roster, request approval/rejection, urgent replacement request, publish update. | MVP | P1 | Kien + Cherry/Gary UI | 12 | 20 | 8 | Resend Email, in-app notifications | notifications, users | POST /notifications/send | Staff receives correct notification for key events. | WhatsApp integration can be delayed. | Build notification UI. | Email/in-app backend. | To discuss
5.1 | ROI/KPI | ROI Dashboard | Admin time saving | A1 roster time saving | Calculate A1 using ROI v2.2: (26h - 7h) × HK$409 = HK$7,771/month. Allow configurable baseline. | Phase 2-4 | P1 | Cherry/Gary + Kien | 12 | 14 | 6 | SQL View, Next.js charts | facilities, survey_input, roster_kpi | GET /roi/admin-time | Dashboard shows formula and assumptions. | Wrong assumptions reduce credibility. | Build ROI cards and text. | Implement calculation and configurable inputs. | To discuss
5.2 | ROI/KPI | ROI Dashboard | Emergency cover saving | A2 SL/DSL saving | Calculate A2: SL/DSL incidents × 0.75h × HK$409. Default March 2026 actual: 46 incidents. | Phase 2-4 | P1 | Kien + Cherry/Gary UI | 10 | 14 | 6 | SQL View | sl_incidents, roster_kpi | GET /roi/emergency-cover | Savings update when SL incidents are logged. | Need clear definition of incident. | Build table/card. | Implement reliable incident logging. | To discuss
5.3 | ROI/KPI | ROI Dashboard | Agency saving | Conservative 5% agency saving | Calculate agency cost saving at 5%, with optional conservative/base/upside scenario table. OT excluded from financial ROI. | Phase 2-4 | P1 | Kien + Cherry/Gary UI | 12 | 16 | 8 | SQL View, dashboard | agency_assignments, facility_budget | GET /roi/agency | Agency saving uses actual agency cost data. | Agency reduction should not be overclaimed. | Build scenario table. | Implement SQL and assumptions. | To discuss
5.4 | ROI/KPI | KPI Framework | Conflict rate | Hard constraint violation KPI | Conflict Rate = Hard Constraint Violations ÷ Total Shift Assignments × 100%. Target: -20% in 6 months. | MVP + Phase 2 | P1 | Kien | 8 | 16 | 8 | OR-Tools, SQL | violation_log, shift_assignments | GET /kpi/conflict-rate | Conflict rate is auto-calculated per roster cycle. | Violation log must be complete. | Build chart. | Implement log and formula. | To discuss
5.5 | ROI/KPI | KPI Framework | AN Gini coefficient | AN fairness KPI | Calculate AN Gini for full-month eligible staff only. Target baseline <0.25, later <0.20 and <=0.10. | Phase 2 | P1 | Kien | 6 | 20 | 10 | Python/Supabase RPC | shift_assignments, staff | GET /kpi/an-gini | AN Gini shown monthly with exclusions. | Formula and inclusion rules must be agreed. | Build chart/table. | Implement Python/SQL calculation. | To discuss
5.6 | ROI/KPI | Model Adoption | Manual override and AI acceptance | AI acceptance tracking | Track how much AI roster is changed by manager. Acceptance = retained AI assignments ÷ total AI assignments. | MVP | P1 | Kien | 8 | 18 | 8 | SQL, dashboard | manual_override_log, roster_versions, shift_assignments | GET /kpi/ai-acceptance | Dashboard shows acceptance and override rate. | Must log every edit. | Build UI cards. | Implement logging middleware. | To discuss
6.1 | Forecast | Staffing Pressure Forecast | Pressure signal v1 | Rule-based pressure score | Do not forecast exact care tasks. Use leave count, SL incidents, agency count, OT/CL, occupancy, special events to score high-pressure shifts. | MVP + Phase 2 | P1 | Kien | 8 | 22 | 10 | SQL scoring, pandas later | pressure_signal, sl_incidents, agency_assignments, leave_requests | GET /pressure/:period | High-pressure shifts are flagged before roster publish. | Avoid overclaiming task-level demand forecast. | Build warning UI. | Define score and data sources. | To discuss
6.2 | Forecast | Weekly Workload Pulse | RN manual workload input | Lightweight manual workload data | RN inputs weekly occupancy, high dependency count, feeding assist count, two-person assist count, special care count, escort count, pressure score. | Phase 2 | P2 | Cherry/Gary + Kien | 16 | 16 | 8 | Next.js form, Supabase | weekly_workload_pulse | POST /workload-pulse | RN can submit weekly workload pulse in 3-5 minutes. | Input burden must be low. | Build form and tooltip. | DB, validation, use in pressure score. | To discuss
6.3 | Forecast | ML Forecast | XGBoost pressure forecast | Train first ML model after data collection | Use XGBoost/Random Forest to predict pressure, agency risk or SL cover risk. Target R² >=0.75 long-term, not MVP. | Phase 3/4 | P2 | Kien | 0 | 32 | 16 | XGBoost, scikit-learn, pandas | pressure_signal, sl_incidents, roster_kpi | POST /models/train; GET /forecast/pressure | Model report shows accuracy and feature importance. | Small RCH dataset may be weak. | Review output labels only. | Model training, evaluation, deployment. | To discuss
7.1 | Reports | PDF/Excel Reports | Roster export | Download schedule and compliance report | Generate roster PDF/Excel, compliance summary, ROI/KPI report for manager and pilot review. | MVP | P1 | Cherry/Gary + Kien | 18 | 24 | 10 | React-pdf, XLSX export, Cloudflare R2 | reports, roster_versions, shift_assignments, roster_kpi | POST /reports/generate | PDF/Excel exports with correct Chinese/English text. | Chinese font rendering. | Design templates and wording. | Data binding, font, file storage. | To discuss
7.2 | Reports | SWD Compliance Reporting | Compliance summary | Generate SWD-style staffing ratio and violation summary | Produce summary of staffing ratio, open gaps, hard violations, certificate warnings, and report timestamp. | MVP + Phase 2 | P1 | Kien + Cherry/Gary UI | 12 | 20 | 8 | React-pdf, SQL views | compliance_rules, violation_log, reports | POST /reports/compliance | Report can be shown to pilot home. | Do not claim official RACAS automation too early. | Layout and wording. | Compliance data and export. | To discuss
8.1 | Admin | User Management | Admin console | View and manage staff/users | Admin can view user list, activate/deactivate users, assign fixed roles, and filter/search staff. | MVP | P1 | Kien + Cherry/Gary UI | 16 | 18 | 8 | Supabase Auth, Next.js | users, staff | GET /users; PATCH /users/:id | Admin can manage users safely. | Role permissions must be simple at MVP. | Build user list UI. | Roles, RLS, APIs. | To discuss
9.1 | Phase 3 | Pareto Optimization | Multi-objective roster | Pareto-style Roster A/B/C | Upgrade A/B/C from fixed soft relaxation to objective-score/Pareto candidate selection: cost, agency, conflict, Gini, preference satisfaction. | Phase 3 | P2 | Kien | 8 | 40 | 20 | CP-SAT + pymoo/DEAP | optimization_runs, roster_kpi | POST /optimize-pareto | System outputs 3 representative options. | Too complex for MVP. | Build comparison UI enhancement. | Algorithm design and runtime. | To discuss
10.1 | Phase 4 | NLP Feedback | Complaint/handover analysis | NLP summary and topic classification | Analyze handover notes, complaints, staff feedback into topics/sentiment and service risk alerts. | Phase 4 | P3 | Kien + Cherry/Gary content | 12 | 32 | 16 | LLM provider, Hugging Face/spaCy | feedback_text | POST /feedback/analyze | Monthly feedback summary generated. | Privacy and hallucination risk. | Define labels and review summaries. | NLP pipeline and security. | To discuss
3.4 | Compliance | Compliance Engine | Daily resident count input | Daily resident count by floor/ward/care level | Superintendent/RN inputs daily resident count by facility, wing, floor/ward and care level. This count is used as the denominator for statutory staffing ratio calculation and reports. | MVP | P0 | Kien + Cherry/Gary UI | 12 | 18 | 8 | Next.js form, Supabase, SQL validation | daily_resident_counts, facilities, wings | POST /resident-counts; GET /resident-counts/:date | Manager can input and edit daily resident counts; compliance engine uses latest count. | Without resident count, staffing ratio cannot be calculated reliably. | Build simple daily input UI and validation messages. | Design DB table, API, validation and audit log. | To discuss
3.5 | Compliance | Compliance Engine | Code of Practice staffing ratio rules | Configurable SWD staffing ratio rule table | Encode Code of Practice staffing ratios by care home type, care level, staff rank and statutory time window. Example: RN 7am–8pm = 1:60; HW 7am–8pm = 1:30; CW 7am–5pm = 1:20 and other times = 1:40; AW 7am–6pm = 1:40; 6pm–7am next day requires at least two staff of any rank. | MVP | P0 | Kien + Cherry/RN validation | 8 | 28 | 14 | Supabase, CP-SAT, rule engine | staffing_ratio_rules, compliance_rules | GET /compliance/rules; POST /compliance/rules | Rules can be configured without code change and reviewed by RN advisor. | Hardcoding only one facility example will create future compliance risk. | Provide rule wording and RN validation. | Implement configurable rule schema and tests. | To discuss
3.6 | Compliance | Compliance Engine | Minute-level staffing ratio calculation | Minute-level overlap between actual shifts and statutory time windows | Compliance engine calculates staff coverage by minute-level overlap because actual shifts may not align with statutory windows. It must count staff only for the minutes they are on duty inside each required time window. | MVP | P0 | Kien | 6 | 36 | 16 | Python/FastAPI, SQL, CP-SAT helper functions | shifts, shift_assignments, staffing_ratio_rules, daily_resident_counts | GET /compliance/minute-ratio | System can prove ratio compliance for any minute/time window in a day. | Most technically difficult compliance logic; must test edge cases. | Help define real shift examples for testing. | Implement minute overlap algorithm and unit tests. | To discuss
3.7 | Compliance | Compliance Reporting | Two staffing ratio report methods | Per-shift and statutory-window ratio reports | Generate two reports: (1) daily per-shift staffing ratio based on actual shifts; (2) daily statutory time-window report based on Code of Practice windows with minute-level overlap. | MVP + Phase 2 | P0/P1 | Kien + Cherry/Gary UI | 14 | 22 | 10 | React-pdf, SQL Views, FastAPI | staffing_ratio_reports, reports, shifts, shift_assignments | POST /reports/staffing-ratio | PDF/Excel report shows both per-shift and statutory-window ratio results. | Report must be clear enough for superintendent and audit use. | Design report layout. | Data aggregation, PDF/Excel export. | To discuss
3.8 | Compliance | Emergency Cover | Replacement suggestion compliance check | Run ratio check before recommending replacement | Urgent replacement suggestions for SL/DSL or last-minute gaps must pass the same staffing ratio compliance check before being recommended. | MVP | P0 | Kien | 6 | 20 | 10 | Rule engine, CP-SAT validation | sl_incidents, shift_assignments, staffing_ratio_rules | GET /replacement-candidates?compliance_checked=true | Suggested replacement list only includes options that do not break staffing ratio rules. | Bad replacement suggestion may create compliance breach. | Help define replacement priority rules. | Implement candidate filtering and ratio validation. | To discuss
5.7 | ROI/KPI | Compliance KPI | SWD staffing ratio compliance KPI | Core compliance KPI for ROI/KPI dashboard | Add staffing ratio compliance as a top-level KPI, not just backend validation. Track ratio breach count, breach minutes, affected shift, affected role, and whether it was resolved before publish. | MVP | P0 | Kien + Cherry/Gary UI | 12 | 18 | 8 | SQL View, Dashboard | staffing_ratio_reports, violation_log, roster_kpi | GET /kpi/staffing-ratio-compliance | Dashboard shows breach count/minutes and pass/fail before publishing roster. | This is central to care home value proposition. | Build KPI cards and trend chart. | Implement calculations and API. | To discuss
5.8 | ROI/KPI | Fairness KPI | All shift-type fairness metrics | Fairness beyond AN Gini | Calculate fairness metrics for every shift type, not only AN: A, P, N, A/N, weekend, PH, and other difficult shifts. Use count distribution, variance or Gini by eligible staff group. | Phase 2 | P1 | Kien + Cherry/Gary UI | 10 | 24 | 12 | Python/Supabase RPC, Dashboard | shift_assignments, staff, roster_kpi | GET /kpi/shift-fairness | Dashboard shows fairness by shift type and staff group. | Need clear inclusion/exclusion rules for agency, joiners, leavers and leave. | Help define which shifts are unpopular/difficult. | Implement formulas and filters. | To discuss
1.3 | Foundation | Database Architecture | Initial schema migration | Supabase schema setup | Apply initial Supabase/PostgreSQL schema covering facilities, units, users, staff contracts, roster versions, shifts, rule profiles, rule definitions, violation log, resident counts, emergency cover and KPI tables. | MVP | P0 | Kien | 2 | 20 | 8 | Supabase PostgreSQL, SQL migrations | all core tables | N/A | Migration runs cleanly; schema supports facility_id and RLS policies. | Poor schema design causes rework. | Review table names with product team. | Create migration, indexes, enums and RLS placeholders. | Synced by Manus 2026-05-30
1.4 | Foundation | Rule Profile Seed | A/B facility seed data | Seed facility-specific rules and demo data | Seed A院舍 and B院舍 facility profiles, shift definitions, rule profiles, staff/contracts, resident counts and demo roster data for frontend integration. | MVP | P0 | Kien + Cherry/Gary | 4 | 20 | 8 | Supabase, SQL seed scripts | facilities, facility_units, shift_definitions, rule_profiles, rule_definitions, staff, staff_contracts | N/A | Frontend can switch between A/B facility profiles and load seeded roster/rules. | Incorrect seed data will misrepresent care-home workflow. | Provide final A/B rules in plain language. | Implement seed scripts and validate with API. | Synced by Manus 2026-05-30
3.9 | Compliance | Rule Builder | Rule CRUD and versioning | Rule Builder backend | Implement facility-scoped Rule Builder CRUD for rule_profiles, rule_definitions, rule_versions and system templates. Rules must be typed, versioned, auditable and testable. | MVP | P0 | Kien | 8 | 28 | 12 | FastAPI, Supabase | rule_profiles, rule_definitions, rule_versions, compliance_rules_seed | GET/POST /rule-profiles; POST/PATCH /rules; GET /rules/templates; POST /rules/:id/test | Manager/admin can create, edit, deactivate and test facility-specific rules. | Rule misconfiguration can block valid rosters. | Provide rule wording and UI labels. | Implement schema, APIs, versioning and rule test endpoint. | Synced by Manus 2026-05-30
3.10 | Compliance | Task Eligibility | Task-code and eligibility validation | Task-code rule engine | Implement task_definitions, task_assignments and eligibility validation for A1-A8/P1-P6, audit restrictions, mentor flags and agency/non-audit task limits. | MVP | P0 | Kien | 8 | 24 | 12 | Rule engine, Supabase | task_definitions, task_assignments, staff_qualifications, violation_log | POST /task-assignments; POST /validate-roster | Non-eligible staff are blocked or logged before task assignment/publish. | A院舍 task code complexity is high. | Confirm task code dictionary. | Build validator and seed task definitions. | Synced by Manus 2026-05-30
4.5 | Staff App | Emergency Cover | Future debt ledger | AN/CL/CO/OT future compensation tracking | Track future debt created by urgent changes: AN make-up, AN credit, CL/CO/OT debt and next-cycle compensation. | MVP | P1 | Kien | 4 | 18 | 8 | Supabase, rule engine | future_debt_ledger, sl_incidents, shift_assignments | GET /future-debt; POST /sl-incidents/:id/resolve | Emergency cover creates future debt entries and next cycle can read them. | If not tracked, AI creates hidden unfairness. | Define debt wording for managers. | Implement ledger and link to emergency resolution. | Synced by Manus 2026-05-30
5.9 | ROI/KPI | External Workforce KPI | External dependency and cap KPI | PT/agency/outsource governance KPI | Track PT/agency/outsource shifts, cost, dependency ratio and external cap violations by role, period and facility. | MVP | P1 | Kien | 6 | 16 | 8 | SQL View, dashboard API | agency_assignments, shift_assignments, staff, facility_budget, violation_log | GET /kpi/external-workforce | Dashboard shows external workforce dependency and cap risk. | External cap rules differ by facility. | Build KPI cards/charts. | Implement SQL/API and rule links. | Synced by Manus 2026-05-30
1.5 | Foundation | Database Architecture | Calendar/Public Holiday | Calendar/Public Holiday & Special Pay Day Schema | Implement calendar_days table for public holidays, statutory holidays, special double-pay days, agency allowance and cost multipliers. This feeds PH/SH handling, agency restrictions, cost calculation and reports. | MVP | P0 | Kien | 4 | 14 | 6 | Supabase PostgreSQL | calendar_days, facility_budget, agency_assignments | GET/POST /calendar-days | Calendar days can be created/loaded and solver can read PH/special-day flags. | Missing holiday calendar causes wrong agency/cost decisions. | Confirm HK PH and facility-specific special days. | Implement table, seed data and API. | Edge Cases Synced by Manus 2026-05-30
1.6 | Foundation | API Contract | Solver payload | Optimize Roster API Payload + Solver Writeback Contract | Define JSON contract between Supabase/Next.js and Python OR-Tools service. Include plan_mode, locked assignments, approved leaves, solver limits, writeback settings, roster option scores and infeasible reasons. | MVP | P0 | Kien | 4 | 18 | 8 | FastAPI, OR-Tools, Supabase | optimization_jobs, roster_versions, shift_assignments, roster_kpi, violation_log | POST /optimize-roster; GET /optimization-jobs/:id | Frontend can call optimizer via stable payload and display A/B/C results. | Vague payload causes frontend/backend rework. | Review payload examples. | Implement OpenAPI schema, job table and writeback. | Edge Cases Synced by Manus 2026-05-30
2.5 | Roster | Roster A/B/C | Soft weights | Roster A/B/C Soft Weight Presets | Implement three soft-weight presets under same hard constraints: A Cost-Optimized, B Staff-Satisfaction, C Balanced/Recommended. Return constraint_score, hard_violation_count, soft_penalty_total and KPI summary. | MVP | P1 | Kien + Cherry/Gary UI | 8 | 18 | 8 | OR-Tools CP-SAT, FastAPI | rule_definitions, optimization_jobs, roster_kpi | POST /optimize-roster | Manager can compare A/B/C with clear score meanings. | Unclear A/B/C makes AI output look arbitrary. | Confirm labels and dashboard wording. | Implement weight presets and scoring output. | Edge Cases Synced by Manus 2026-05-30
3.11 | Compliance | OR-Tools Engine | Hard constraints | OR-Tools Hard Constraint Mapping | Map MVP hard constraints into OR-Tools variables and Add() constraints: overlap, leave unavailability, coverage, SWD ratio, rest gap, imported labor rest, max hours, task eligibility and hard external caps. | MVP | P0 | Kien | 4 | 36 | 16 | OR-Tools CP-SAT, Python | rule_definitions, shifts, shift_assignments, staff_contracts, staff_qualifications, daily_resident_counts | POST /validate-roster; POST /optimize-roster | Hard constraints produce deterministic pass/fail and infeasible reasons. | If hard constraints are treated as soft warnings, roster may be illegal. | Clarify rule wording with RN/operator. | Implement variable map, Add() constraints and tests. | Edge Cases Synced by Manus 2026-05-30
3.12 | Compliance | Solver Output | Scoring and writeback | Solver Output Scoring & Writeback | Persist solver output as candidate roster_versions with constraint_score, hard_violation_count, soft_penalty_total, plan_mode, objective_weights_json and infeasible_reasons_json for frontend comparison. | MVP | P0 | Kien | 4 | 20 | 10 | FastAPI, Supabase | optimization_jobs, roster_versions, roster_kpi, violation_log | GET /optimization-jobs/:id | Roster options are persisted and auditable with scores and reasons. | Without writeback, frontend cannot compare or publish solver results. | Confirm dashboard score labels. | Implement writeback and KPI linkage. | Edge Cases Synced by Manus 2026-05-30

## Project breakdown 中文
No | Feature | Module | Sub-module | Function | Detail / Requirement | MVP / Phase | Priority | Owner | FE Est | BE Est | Test Est | Tools | Database Tables | API / Endpoint | Acceptance Criteria | Risk / Question | Cherry/Gary Can Help | Kien Must Handle | Status
1.1 | 基礎建設 | 登入與權限 | Supabase 登入設定 | Supabase Auth setup | Email/password login, forgot password, reset password, role-based login for Superintendent, Admin, Staff. Use Supabase Auth rather than custom password logic. | MVP | P0 | Kien + Cherry/Gary UI | 8 | 12 | 6 | Supabase Auth, Next.js | users, facilities | POST /auth/login; POST /auth/reset | Users can login and are redirected based on role. | RLS and role mapping must be correct before pilot. | Build login/reset UI and empty states. | Configure Supabase Auth, JWT, roles, RLS policies. | 待與 Kien 確認
1.2 | 基礎建設 | 多院舍資料隔離 | Facility isolation | facility_id 與 RLS 權限 | Every core table must include facility_id. Care home A must not see care home B data. | MVP | P0 | Kien | 2 | 16 | 8 | Supabase PostgreSQL, RLS | all core tables | N/A | RLS test confirms cross-facility access is blocked. | Data leakage is critical risk. | Prepare facility selector UI only. | Design RLS policies and test cases. | 待與 Kien 確認
2.1 | 更表 | 更表管理 | 週/月更表視圖 | 週更表與月更表 | Display 7-day and 28-day roster with staff rank, wing/floor, shift type, shift tasks as display labels, status, worked hours. | MVP | P0 | Cherry/Gary + Kien | 24 | 14 | 8 | Next.js, Tailwind, shadcn/ui | roster_versions, shifts, shift_assignments, staff | GET /rosters/:period | Roster page shows real DB data, not mock data. | Prototype mock data may not match DB schema. | Improve existing prototype roster UI. | Provide API and data mapping. | 待與 Kien 確認
2.2 | 更表 | 更表管理 | 建立/修改更份 | 手動更份 CRUD | Manager can create A/P/N/AN/AL/OFF/SLEEP shifts, edit shift time, wing, required role, and assign/unassign staff. | MVP | P0 | Kien + Cherry/Gary UI | 20 | 24 | 10 | Next.js, FastAPI/Supabase | shifts, shift_assignments | POST /shifts; PATCH /shifts/:id; DELETE /shifts/:id | Manager can create, edit, delete, assign and unassign shifts. | Manual edits must be logged for AI acceptance rate. | Build modal and forms. | Implement APIs and manual_override_log. | 待與 Kien 確認
2.3 | 更表 | 更表管理 | 儲存與發布 | 更表版本流程 | Save draft roster, publish selected roster, lock published version, allow rollback to previous published roster. | MVP | P0 | Kien | 8 | 20 | 8 | Supabase, FastAPI | roster_versions, reports, audit_log | POST /rosters/save; POST /rosters/publish | Published roster becomes visible to staff app. | Wrong publish could affect real operations. | Build buttons and confirmation UI. | Versioning, rollback, audit log. | 待與 Kien 確認
2.4 | 更表 | 名冊 A/B/C | 三方案比較 | Generate and compare Roster A/B/C | MVP may use CP-SAT with different soft weights. Show cost, agency shifts, OT/CL dashboard, preference score, compliance status. | MVP | P0 | Kien + Cherry/Gary UI | 20 | 32 | 12 | OR-Tools CP-SAT, FastAPI, Next.js | optimization_runs, roster_versions, roster_kpi | POST /optimize-roster | Manager can compare three roster options. | Runtime may exceed 60 seconds; need job status. | Build comparison cards/table. | 3-plan engine, objective scores, job handling. | 待與 Kien 確認
3.1 | 合規 | 合規引擎 | H1-H13 硬性約束 | 規則映射 | Translate H1-H13 and SWD staffing ratio rules into machine-checkable constraints and violation logs. | MVP | P0 | Kien | 8 | 36 | 16 | OR-Tools CP-SAT, Supabase | compliance_rules, violation_log, shifts, shift_assignments | GET /compliance; POST /validate-roster | Hard constraint violations are listed clearly. | LLM must not be used as hard-constraint validator. | Build violation cards and warning UI. | Implement rules, tests, severity levels. | 待與 Kien 確認
3.2 | 合規 | 合規 Dashboard | 人手比例 | 按更次/翼/職級計算比例 | Calculate RN/HW/CW/AW ratio by shift and wing, matching prototype Staffing Ratio card. | MVP | P0 | Kien + Cherry/Gary UI | 12 | 18 | 8 | SQL View, FastAPI, Next.js | facilities, wings, shifts, shift_assignments, staff | GET /compliance/ratio | Dashboard shows ratio and whether it meets minimum standard. | Resident count may be manually updated; need source of truth. | Build dashboard stat cards. | Implement ratio SQL/API and edge cases. | 待與 Kien 確認
3.3 | 合規 | AN/PH/AL 規則 | 通宵/假期合規 | AN limit, sleeping day, rest day and PH handling | Track AN count, sleeping day, rest day, public holiday, AL balance, and warning rules. | MVP + Phase 2 | P0/P1 | Kien | 8 | 28 | 12 | CP-SAT, SQL, Python optional | leave_requests, shift_assignments, roster_kpi | GET /compliance/an; GET /leave/balance | AN over-limit and missing rest rules are detected. | AN rules are operationally complex; confirm with RN advisor. | Help define nursing rules in plain language. | Implement logic and tests. | 待與 Kien 確認
4.1 | 員工 App | 員工查更 | 查看個人更表 | Staff can view own roster | Staff can view shift details, shift status, wing/floor, role, task labels, and download own schedule. | MVP | P0 | Cherry/Gary + Kien | 24 | 12 | 8 | Next.js PWA, Supabase Auth | staff, shift_assignments, shifts | GET /staff/me/roster | Staff only sees own roster. | Permission errors could expose other staff schedules. | Build mobile screens. | Auth, permission, API filters. | 待與 Kien 確認
4.2 | 員工 App | 假期申請 | 年假/休息日/指定更申請 | Submit and track requests | Staff can submit AL/day-off/specific duty request before roster cutoff; manager can approve/reject. | MVP | P0 | Kien + Cherry/Gary UI | 24 | 20 | 10 | Next.js PWA, Supabase | leave_requests, notifications | POST /leave-requests; PATCH /leave-requests/:id | Request lifecycle works: pending, approved, rejected. | Approval must update roster if needed. | Build forms and lists. | State transitions, APIs, audit. | 待與 Kien 確認
4.3 | 員工 App | 緊急病假/特別假 | 緊急請假與補更 | Submit urgent SL/DSL and trigger replacement suggestion | Staff submits urgent sick/special leave for upcoming shift; manager receives alert; system suggests available replacement candidates. | MVP | P0 | Kien + Cherry/Gary UI | 20 | 30 | 12 | Rule engine, notification | sl_incidents, leave_requests, shift_assignments, staff | POST /sl-incidents; GET /replacement-candidates | SL incident is logged and replacement candidates are shown. | Directly affects ROI A2; data must be accurate. | Build request/approval UI. | Matching rules, alerts, ROI logging. | 待與 Kien 確認
4.4 | 員工 App | 通知 | App/Email 通知 | Shift and request notifications | Notify staff for new roster, request approval/rejection, urgent replacement request, publish update. | MVP | P1 | Kien + Cherry/Gary UI | 12 | 20 | 8 | Resend Email, in-app notifications | notifications, users | POST /notifications/send | Staff receives correct notification for key events. | WhatsApp integration can be delayed. | Build notification UI. | Email/in-app backend. | 待與 Kien 確認
5.1 | ROI/KPI | ROI Dashboard | 行政時間節省 | A1 roster time saving | Calculate A1 using ROI v2.2: (26h - 7h) × HK$409 = HK$7,771/month. Allow configurable baseline. | Phase 2-3 | P1 | Cherry/Gary + Kien | 12 | 14 | 6 | SQL View, Next.js charts | facilities, survey_input, roster_kpi | GET /roi/admin-time | Dashboard shows formula and assumptions. | Wrong assumptions reduce credibility. | Build ROI cards and text. | Implement calculation and configurable inputs. | 待與 Kien 確認
5.2 | ROI/KPI | ROI Dashboard | 緊急補更節省 | A2 SL/DSL saving | Calculate A2: SL/DSL incidents × 0.75h × HK$409. Default March 2026 actual: 46 incidents. | Phase 2-3 | P1 | Kien + Cherry/Gary UI | 10 | 14 | 6 | SQL View | sl_incidents, roster_kpi | GET /roi/emergency-cover | Savings update when SL incidents are logged. | Need clear definition of incident. | Build table/card. | Implement reliable incident logging. | 待與 Kien 確認
5.3 | ROI/KPI | ROI Dashboard | Agency 節省 | Conservative 5% agency saving | Calculate agency cost saving at 5%, with optional conservative/base/upside scenario table. OT excluded from financial ROI. | Phase 2-3 | P1 | Kien + Cherry/Gary UI | 12 | 16 | 8 | SQL View, dashboard | agency_assignments, facility_budget | GET /roi/agency | Agency saving uses actual agency cost data. | Agency reduction should not be overclaimed. | Build scenario table. | Implement SQL and assumptions. | 待與 Kien 確認
5.4 | ROI/KPI | KPI 框架 | 衝突率 | Hard constraint violation KPI | Conflict Rate = Hard Constraint Violations ÷ Total Shift Assignments × 100%. Target: -20% in 6 months. | MVP + Phase 2 | P1 | Kien | 8 | 16 | 8 | OR-Tools, SQL | violation_log, shift_assignments | GET /kpi/conflict-rate | Conflict rate is auto-calculated per roster cycle. | Violation log must be complete. | Build chart. | Implement log and formula. | 待與 Kien 確認
5.5 | ROI/KPI | KPI 框架 | AN 公平性 Gini | AN fairness KPI | Calculate AN Gini for full-month eligible staff only. Target baseline <0.25, later <0.20 and <=0.10. | MVP | P1 | Kien | 6 | 20 | 10 | Python/Supabase RPC | shift_assignments, staff | GET /kpi/an-gini | AN Gini shown monthly with exclusions. | Formula and inclusion rules must be agreed. | Build chart/table. | Implement Python/SQL calculation. | 待與 Kien 確認
5.6 | ROI/KPI | AI 採用率 | 手動修改與 AI 接受率 | AI acceptance tracking | Track how much AI roster is changed by manager. Acceptance = retained AI assignments ÷ total AI assignments. | Phase 2-4 | P1 | Kien | 8 | 18 | 8 | SQL, dashboard | manual_override_log, roster_versions, shift_assignments | GET /kpi/ai-acceptance | Dashboard shows acceptance and override rate. | Must log every edit. | Build UI cards. | Implement logging middleware. | 待與 Kien 確認
6.1 | 預測 | 人手壓力預測 | 人手壓力訊號 v1 | 規則式壓力分數 | Do not forecast exact care tasks. Use leave count, SL incidents, agency count, OT/CL, occupancy, special events to score high-pressure shifts. | MVP + Phase 2 | P1 | Kien | 8 | 22 | 10 | SQL scoring, pandas later | pressure_signal, sl_incidents, agency_assignments, leave_requests | GET /pressure/:period | High-pressure shifts are flagged before roster publish. | Avoid overclaiming task-level demand forecast. | Build warning UI. | Define score and data sources. | 待與 Kien 確認
6.2 | 預測 | 每週工作量脈搏 | RN 手動輸入簡化工作量 | Lightweight manual workload data | RN inputs weekly occupancy, high dependency count, feeding assist count, two-person assist count, special care count, escort count, pressure score. | Phase 2 | P2 | Cherry/Gary + Kien | 16 | 16 | 8 | Next.js form, Supabase | weekly_workload_pulse | POST /workload-pulse | RN can submit weekly workload pulse in 3-5 minutes. | Input burden must be low. | Build form and tooltip. | DB, validation, use in pressure score. | 待與 Kien 確認
6.3 | 預測 | 機器學習預測 | XGBoost 人手壓力預測 | Train first ML model after data collection | Use XGBoost/Random Forest to predict pressure, agency risk or SL cover risk. Target R² >=0.75 long-term, not MVP. | Phase 3/4 | P2 | Kien | 0 | 32 | 16 | XGBoost, scikit-learn, pandas | pressure_signal, sl_incidents, roster_kpi | POST /models/train; GET /forecast/pressure | Model report shows accuracy and feature importance. | Small RCH dataset may be weak. | Review output labels only. | Model training, evaluation, deployment. | 待與 Kien 確認
7.1 | 報告 | PDF/Excel 報告 | 更表輸出 | Download schedule and compliance report | Generate roster PDF/Excel, compliance summary, ROI/KPI report for manager and pilot review. | MVP | P1 | Cherry/Gary + Kien | 18 | 24 | 10 | React-pdf, XLSX export, Cloudflare R2 | reports, roster_versions, shift_assignments, roster_kpi | POST /reports/generate | PDF/Excel exports with correct Chinese/English text. | Chinese font rendering. | Design templates and wording. | Data binding, font, file storage. | 待與 Kien 確認
7.2 | 報告 | SWD 合規報告 | 合規摘要 | Generate SWD-style staffing ratio and violation summary | Produce summary of staffing ratio, open gaps, hard violations, certificate warnings, and report timestamp. | MVP + Phase 2 | P1 | Kien + Cherry/Gary UI | 12 | 20 | 8 | React-pdf, SQL views | compliance_rules, violation_log, reports | POST /reports/compliance | Report can be shown to pilot home. | Do not claim official RACAS automation too early. | Layout and wording. | Compliance data and export. | 待與 Kien 確認
8.1 | 管理 | 用戶管理 | 管理後台 | View and manage staff/users | Admin can view user list, activate/deactivate users, assign fixed roles, and filter/search staff. | MVP | P1 | Kien + Cherry/Gary UI | 16 | 18 | 8 | Supabase Auth, Next.js | users, staff | GET /users; PATCH /users/:id | Admin can manage users safely. | Role permissions must be simple at MVP. | Build user list UI. | Roles, RLS, APIs. | 待與 Kien 確認
9.1 | Phase 3 | Pareto 多目標優化 | 多目標更表 | Pareto-style Roster A/B/C | Upgrade A/B/C from fixed soft relaxation to objective-score/Pareto candidate selection: cost, agency, conflict, Gini, preference satisfaction. | Phase 3 | P2 | Kien | 8 | 40 | 20 | CP-SAT + pymoo/DEAP | optimization_runs, roster_kpi | POST /optimize-pareto | System outputs 3 representative options. | Too complex for MVP. | Build comparison UI enhancement. | Algorithm design and runtime. | 待與 Kien 確認
10.1 | Phase 4 | NLP 回饋 | 投訴/交更分析 | NLP summary and topic classification | Analyze handover notes, complaints, staff feedback into topics/sentiment and service risk alerts. | Phase 4 | P3 | Kien + Cherry/Gary content | 12 | 32 | 16 | LLM provider, Hugging Face/spaCy | feedback_text | POST /feedback/analyze | Monthly feedback summary generated. | Privacy and hallucination risk. | Define labels and review summaries. | NLP pipeline and security. | 待與 Kien 確認
3.4 | 合規 | 合規引擎 | 每日院友數輸入 | 按樓層/ward/照顧程度輸入每日院友數 | Superintendent/RN inputs daily resident count by facility, wing, floor/ward and care level. This count is used as the denominator for statutory staffing ratio calculation and reports. | MVP | P0 | Kien + Cherry/Gary UI | 12 | 18 | 8 | Next.js form, Supabase, SQL validation | daily_resident_counts, facilities, wings | POST /resident-counts; GET /resident-counts/:date | Manager can input and edit daily resident counts; compliance engine uses latest count. | Without resident count, staffing ratio cannot be calculated reliably. | Build simple daily input UI and validation messages. | Design DB table, API, validation and audit log. | 待與 Kien 確認
3.5 | 合規 | 合規引擎 | 安老院實務守則人手比例規則 | 可配置社署人手比例規則表 | Encode Code of Practice staffing ratios by care home type, care level, staff rank and statutory time window. Example: RN 7am–8pm = 1:60; HW 7am–8pm = 1:30; CW 7am–5pm = 1:20 and other times = 1:40; AW 7am–6pm = 1:40; 6pm–7am next day requires at least two staff of any rank. | MVP | P0 | Kien + Cherry/RN validation | 8 | 28 | 14 | Supabase, CP-SAT, rule engine | staffing_ratio_rules, compliance_rules | GET /compliance/rules; POST /compliance/rules | Rules can be configured without code change and reviewed by RN advisor. | Hardcoding only one facility example will create future compliance risk. | Provide rule wording and RN validation. | Implement configurable rule schema and tests. | 待與 Kien 確認
3.6 | 合規 | 合規引擎 | 分鐘級人手比例計算 | 實際更期與法定時間窗的分鐘級重疊計算 | Compliance engine calculates staff coverage by minute-level overlap because actual shifts may not align with statutory windows. It must count staff only for the minutes they are on duty inside each required time window. | MVP | P0 | Kien | 6 | 36 | 16 | Python/FastAPI, SQL, CP-SAT helper functions | shifts, shift_assignments, staffing_ratio_rules, daily_resident_counts | GET /compliance/minute-ratio | System can prove ratio compliance for any minute/time window in a day. | Most technically difficult compliance logic; must test edge cases. | Help define real shift examples for testing. | Implement minute overlap algorithm and unit tests. | 待與 Kien 確認
3.7 | 合規 | 合規報告 | 兩種人手比例報告方法 | 每更比例及法定時間段比例報告 | Generate two reports: (1) daily per-shift staffing ratio based on actual shifts; (2) daily statutory time-window report based on Code of Practice windows with minute-level overlap. | MVP + Phase 2 | P0/P1 | Kien + Cherry/Gary UI | 14 | 22 | 10 | React-pdf, SQL Views, FastAPI | staffing_ratio_reports, reports, shifts, shift_assignments | POST /reports/staffing-ratio | PDF/Excel report shows both per-shift and statutory-window ratio results. | Report must be clear enough for superintendent and audit use. | Design report layout. | Data aggregation, PDF/Excel export. | 待與 Kien 確認
3.8 | 合規 | 緊急補更 | 替假建議合規檢查 | 推薦替更人手前先做人手比例檢查 | Urgent replacement suggestions for SL/DSL or last-minute gaps must pass the same staffing ratio compliance check before being recommended. | MVP | P0 | Kien | 6 | 20 | 10 | Rule engine, CP-SAT validation | sl_incidents, shift_assignments, staffing_ratio_rules | GET /replacement-candidates?compliance_checked=true | Suggested replacement list only includes options that do not break staffing ratio rules. | Bad replacement suggestion may create compliance breach. | Help define replacement priority rules. | Implement candidate filtering and ratio validation. | 待與 Kien 確認
5.7 | ROI/KPI | 合規 KPI | 社署人手比例合規 KPI | ROI/KPI Dashboard 核心合規指標 | Add staffing ratio compliance as a top-level KPI, not just backend validation. Track ratio breach count, breach minutes, affected shift, affected role, and whether it was resolved before publish. | MVP | P0 | Kien + Cherry/Gary UI | 12 | 18 | 8 | SQL View, Dashboard | staffing_ratio_reports, violation_log, roster_kpi | GET /kpi/staffing-ratio-compliance | Dashboard shows breach count/minutes and pass/fail before publishing roster. | This is central to care home value proposition. | Build KPI cards and trend chart. | Implement calculations and API. | 待與 Kien 確認
5.8 | ROI/KPI | 公平性 KPI | 所有更份公平性指標 | 不止 AN Gini 的公平性計算 | Calculate fairness metrics for every shift type, not only AN: A, P, N, A/N, weekend, PH, and other difficult shifts. Use count distribution, variance or Gini by eligible staff group. | Phase 2 | P1 | Kien + Cherry/Gary UI | 10 | 24 | 12 | Python/Supabase RPC, Dashboard | shift_assignments, staff, roster_kpi | GET /kpi/shift-fairness | Dashboard shows fairness by shift type and staff group. | Need clear inclusion/exclusion rules for agency, joiners, leavers and leave. | Help define which shifts are unpopular/difficult. | Implement formulas and filters. | 待與 Kien 確認
1.3 | 基礎建設 | 資料庫架構 | Initial schema migration | Supabase schema setup | Apply initial Supabase/PostgreSQL schema covering facilities, units, users, staff contracts, roster versions, shifts, rule profiles, rule definitions, violation log, resident counts, emergency cover and KPI tables. | MVP | P0 | Kien | 2 | 20 | 8 | Supabase PostgreSQL, SQL migrations | all core tables | N/A | Migration runs cleanly; schema supports facility_id and RLS policies. | Poor schema design causes rework. | Review table names with product team. | Create migration, indexes, enums and RLS placeholders. | Synced by Manus 2026-05-30
1.4 | 基礎建設 | 院舍規則種子資料 | A/B facility seed data | Seed facility-specific rules and demo data | Seed A院舍 and B院舍 facility profiles, shift definitions, rule profiles, staff/contracts, resident counts and demo roster data for frontend integration. | MVP | P0 | Kien + Cherry/Gary | 4 | 20 | 8 | Supabase, SQL seed scripts | facilities, facility_units, shift_definitions, rule_profiles, rule_definitions, staff, staff_contracts | N/A | Frontend can switch between A/B facility profiles and load seeded roster/rules. | Incorrect seed data will misrepresent care-home workflow. | Provide final A/B rules in plain language. | Implement seed scripts and validate with API. | Synced by Manus 2026-05-30
3.9 | 合規 | Rule Builder | Rule CRUD and versioning | Rule Builder backend | Implement facility-scoped Rule Builder CRUD for rule_profiles, rule_definitions, rule_versions and system templates. Rules must be typed, versioned, auditable and testable. | MVP | P0 | Kien | 8 | 28 | 12 | FastAPI, Supabase | rule_profiles, rule_definitions, rule_versions, compliance_rules_seed | GET/POST /rule-profiles; POST/PATCH /rules; GET /rules/templates; POST /rules/:id/test | Manager/admin can create, edit, deactivate and test facility-specific rules. | Rule misconfiguration can block valid rosters. | Provide rule wording and UI labels. | Implement schema, APIs, versioning and rule test endpoint. | Synced by Manus 2026-05-30
3.10 | 合規 | Task-code資格限制 | Task-code and eligibility validation | Task-code rule engine | Implement task_definitions, task_assignments and eligibility validation for A1-A8/P1-P6, audit restrictions, mentor flags and agency/non-audit task limits. | MVP | P0 | Kien | 8 | 24 | 12 | Rule engine, Supabase | task_definitions, task_assignments, staff_qualifications, violation_log | POST /task-assignments; POST /validate-roster | Non-eligible staff are blocked or logged before task assignment/publish. | A院舍 task code complexity is high. | Confirm task code dictionary. | Build validator and seed task definitions. | Synced by Manus 2026-05-30
4.5 | 員工 App | 緊急補更 | Future debt ledger | AN/CL/CO/OT future compensation tracking | Track future debt created by urgent changes: AN make-up, AN credit, CL/CO/OT debt and next-cycle compensation. | MVP | P1 | Kien | 4 | 18 | 8 | Supabase, rule engine | future_debt_ledger, sl_incidents, shift_assignments | GET /future-debt; POST /sl-incidents/:id/resolve | Emergency cover creates future debt entries and next cycle can read them. | If not tracked, AI creates hidden unfairness. | Define debt wording for managers. | Implement ledger and link to emergency resolution. | Synced by Manus 2026-05-30
5.9 | ROI/KPI | 外部人手KPI | External dependency and cap KPI | PT/agency/outsource governance KPI | Track PT/agency/outsource shifts, cost, dependency ratio and external cap violations by role, period and facility. | MVP | P1 | Kien | 6 | 16 | 8 | SQL View, dashboard API | agency_assignments, shift_assignments, staff, facility_budget, violation_log | GET /kpi/external-workforce | Dashboard shows external workforce dependency and cap risk. | External cap rules differ by facility. | Build KPI cards/charts. | Implement SQL/API and rule links. | Synced by Manus 2026-05-30
1.5 | 基礎建設 | 資料庫架構 | 日曆/公眾假期 | Calendar/Public Holiday & Special Pay Day Schema | Implement calendar_days table for public holidays, statutory holidays, special double-pay days, agency allowance and cost multipliers. This feeds PH/SH handling, agency restrictions, cost calculation and reports. | MVP | P0 | Kien | 4 | 14 | 6 | Supabase PostgreSQL | calendar_days, facility_budget, agency_assignments | GET/POST /calendar-days | Calendar days can be created/loaded and solver can read PH/special-day flags. | Missing holiday calendar causes wrong agency/cost decisions. | Confirm HK PH and facility-specific special days. | Implement table, seed data and API. | Edge Cases Synced by Manus 2026-05-30
1.6 | 基礎建設 | API合約 | Solver payload | Optimize Roster API Payload + Solver Writeback Contract | Define JSON contract between Supabase/Next.js and Python OR-Tools service. Include plan_mode, locked assignments, approved leaves, solver limits, writeback settings, roster option scores and infeasible reasons. | MVP | P0 | Kien | 4 | 18 | 8 | FastAPI, OR-Tools, Supabase | optimization_jobs, roster_versions, shift_assignments, roster_kpi, violation_log | POST /optimize-roster; GET /optimization-jobs/:id | Frontend can call optimizer via stable payload and display A/B/C results. | Vague payload causes frontend/backend rework. | Review payload examples. | Implement OpenAPI schema, job table and writeback. | Edge Cases Synced by Manus 2026-05-30
2.5 | 更表 | Roster A/B/C | Soft weights | Roster A/B/C Soft Weight Presets | Implement three soft-weight presets under same hard constraints: A Cost-Optimized, B Staff-Satisfaction, C Balanced/Recommended. Return constraint_score, hard_violation_count, soft_penalty_total and KPI summary. | MVP | P1 | Kien + Cherry/Gary UI | 8 | 18 | 8 | OR-Tools CP-SAT, FastAPI | rule_definitions, optimization_jobs, roster_kpi | POST /optimize-roster | Manager can compare A/B/C with clear score meanings. | Unclear A/B/C makes AI output look arbitrary. | Confirm labels and dashboard wording. | Implement weight presets and scoring output. | Edge Cases Synced by Manus 2026-05-30
3.11 | 合規 | OR-Tools引擎 | Hard constraints | OR-Tools Hard Constraint Mapping | Map MVP hard constraints into OR-Tools variables and Add() constraints: overlap, leave unavailability, coverage, SWD ratio, rest gap, imported labor rest, max hours, task eligibility and hard external caps. | MVP | P0 | Kien | 4 | 36 | 16 | OR-Tools CP-SAT, Python | rule_definitions, shifts, shift_assignments, staff_contracts, staff_qualifications, daily_resident_counts | POST /validate-roster; POST /optimize-roster | Hard constraints produce deterministic pass/fail and infeasible reasons. | If hard constraints are treated as soft warnings, roster may be illegal. | Clarify rule wording with RN/operator. | Implement variable map, Add() constraints and tests. | Edge Cases Synced by Manus 2026-05-30
3.12 | 合規 | Solver輸出 | Scoring and writeback | Solver Output Scoring & Writeback | Persist solver output as candidate roster_versions with constraint_score, hard_violation_count, soft_penalty_total, plan_mode, objective_weights_json and infeasible_reasons_json for frontend comparison. | MVP | P0 | Kien | 4 | 20 | 10 | FastAPI, Supabase | optimization_jobs, roster_versions, roster_kpi, violation_log | GET /optimization-jobs/:id | Roster options are persisted and auditable with scores and reasons. | Without writeback, frontend cannot compare or publish solver results. | Confirm dashboard score labels. | Implement writeback and KPI linkage. | Edge Cases Synced by Manus 2026-05-30

## DB Schema
Table | Key Fields | Purpose | Phase | Owner | Related Feature | Notes / Risk
facilities | facility_id, name, type, resident_count, wings, timezone | Facility profile | MVP | Kien | All modules | resident_count may be manual at MVP
users | user_id, email, role, facility_id, auth_id | Login and roles | MVP | Kien | Authentication | Use Supabase Auth + RLS
staff | staff_id, facility_id, name, rank, employment_type, contracted_hours, status | Staff profile | MVP | Kien | Roster, Staff App | Rank values must match compliance rules
staff_certificates | cert_id, staff_id, cert_type, expiry_date, file_url | Certificate and expiry alerts | Phase 2 | Kien | Compliance Alert | Can delay file upload if needed
shifts | shift_id, facility_id, date, shift_type, start_time, end_time, wing, required_rank | Shift records | MVP | Kien | Roster | Core CP-SAT input
shift_assignments | assignment_id, shift_id, staff_id, role, status, is_agency | Staff-to-shift assignments | MVP | Kien | Roster, KPI | Core roster output
roster_versions | roster_id, period_start, period_end, version_type, status, created_by | Roster A/B/C and publish control | MVP | Kien | Roster A/B/C | Needed for rollback and publish
leave_requests | request_id, staff_id, leave_type, date_start, date_end, status, reason | AL/SL/DSL/day off requests | MVP | Kien | Leave | Affects availability
sl_incidents | incident_id, staff_id, shift_id, type, created_at, replacement_status | Emergency cover ROI Part A2 | MVP | Kien | Emergency Cover | Directly supports ROI
agency_assignments | agency_id, shift_id, role, cost, vendor, reason | Agency cost saving | MVP | Kien | ROI | Needed for 5% agency saving
compliance_rules | rule_id, code, description, severity, active | H1-H13 / SWD rules | MVP | Kien | Compliance | Versioning later
violation_log | violation_id, roster_id, rule_id, shift_id, severity, resolved | Hard constraint violations | MVP | Kien | Compliance KPI | Needed for conflict rate
pressure_signal | shift_id, leave_count, agency_count, ot_hours, occupancy, event_flag, score | Staffing Pressure Forecast | MVP / Phase 2 | Kien | Forecast | Rule-based first, ML later
roster_kpi | roster_id, admin_hours, agency_cost, conflict_rate, gini, override_rate | ROI/KPI tracking | MVP | Kien | ROI/KPI | Use for pilot proof
manual_override_log | override_id, roster_id, assignment_id, changed_by, reason | AI adoption and override rate | MVP | Kien | Model Adoption | Log every manager edit
reports | report_id, type, period, file_url, generated_by | PDF/Excel reports | MVP | Kien | Reports | Cloudflare R2 optional
weekly_workload_pulse | week, wing, occupancy, high_dependency_count, feeding_assist_count, pressure_score | Lightweight workload input | Phase 2 | Cherry/Gary UI + Kien | Forecast | No nursing system integration needed
feedback_text | feedback_id, source, text, topic, sentiment, related_shift | NLP feedback | Phase 4 | Kien | NLP | Sensitive data; PDPO controls needed
daily_resident_counts | count_id, facility_id, date, wing, floor, ward, care_level, resident_count, entered_by, updated_at | Daily resident count denominator for staffing ratio calculation | MVP | Kien | Compliance | Required for accurate SWD staffing ratio calculation
staffing_ratio_rules | rule_id, facility_type, care_level, staff_rank, time_window_start, time_window_end, ratio_residents_per_staff, min_staff_any_rank, effective_from, active | Configurable Code of Practice staffing ratio rules | MVP | Kien + RN validation | Compliance | Do not hardcode only one facility example
staffing_ratio_reports | report_id, roster_id, date, report_type, wing, floor, ward, staff_rank, required_staff, actual_staff_minutes, breach_minutes, pass_fail | Stores per-shift and statutory-window ratio report outputs | MVP / Phase 2 | Kien | Reporting | Supports audit and superintendent review
shift_fairness_metrics | metric_id, roster_id, period, shift_type, staff_group, gini, variance, max_count, min_count, calculated_at | Fairness metrics for every shift type, not only AN | Phase 2 | Kien | ROI/KPI | A/P/N/A-N/weekend/PH fairness dashboard
facility_units | unit_id, facility_id, parent_unit_id, unit_type, name, code | Facility wing/floor/ward/cubicle hierarchy | MVP | Kien | Compliance, Roster | Needed for floor/ward ratio and task coverage
users_profile | user_profile_id, auth_user_id, facility_id, email, role, staff_id | User profile linked to Supabase Auth | MVP | Kien | Auth, RLS | Use instead of overloading auth user metadata only
staff_contracts | contract_id, staff_id, weekly_hours, max_weekly_hours, min_rest_minutes, allowed_shift_types | Staff contract and rest rules | MVP | Kien | Compliance, Solver | Core input for rest/hour constraints
staff_qualifications | qualification_id, staff_id, qualification_type, value, effective_from, effective_to | Audit/mentor/task eligibility | MVP | Kien | Rule Builder, Task Code | Needed for non-audit and mentor logic
staff_availability | availability_id, staff_id, date, start_time, end_time, availability_type, source | Availability and agency preference | MVP | Kien | Roster, Emergency Cover | Supports replacement candidates
external_vendors | vendor_id, facility_id, name, vendor_type, contact_json | Agency/outsource vendors | MVP | Kien | External Workforce | Needed for agency assignments
external_worker_rates | rate_id, staff_id, shift_type, weekday_rate, night_rate, ph_multiplier | External worker cost rates | MVP | Kien | ROI/KPI, Cost | Supports agency cost and premium PH/N
roster_periods | period_id, facility_id, period_start, period_end, cycle_type, status | Roster planning period | MVP | Kien | Roster | Separates 28-day and natural-month cycle
shift_definitions | definition_id, facility_id, shift_type, label, start_time, end_time, paid_minutes, cross_midnight | Facility shift dictionary | MVP | Kien | Rule Builder, Roster | Needed for A/B/E/P/N/AN/7A/7P/9A/9P
task_definitions | task_id, facility_id, task_code, task_name, shift_type, required_rank, requires_audit | Task code dictionary | MVP | Kien | Task Code | A1-A8/P1-P6 support
task_assignments | task_assignment_id, shift_assignment_id, task_id, task_status | Assign staff to task codes | MVP | Kien | Roster, Compliance | Task coverage and eligibility validation
rule_profiles | profile_id, facility_id, name, status, effective_from, version | Facility active rule set | MVP | Kien | Rule Builder | A/B facility-specific rules
rule_definitions | rule_id, facility_id, profile_id, rule_code, rule_type, severity, config_json | Rule Builder records | MVP | Kien | Rule Builder, Compliance | Core configurable rules table
rule_versions | version_id, rule_id, version, config_json, changed_by, created_at | Rule version history | MVP | Kien | Rule Builder | Auditability for rule changes
roster_publish_events | event_id, roster_version_id, event_type, created_by, created_at | Publish/rollback audit | MVP | Kien | Roster Versioning | Required for publish control
replacement_candidates | candidate_id, incident_id, candidate_staff_id, score, rank, blocked_reasons, future_debt_json | Emergency replacement candidate snapshot | MVP | Kien | Emergency Cover | Stores candidate ranking used by manager
future_debt_ledger | debt_id, staff_id, debt_type, quantity, due_period_id, status | Future AN/CL/CO/OT compensation debt | MVP | Kien | Emergency, Fairness | Needed for next-cycle fairness
facility_events | event_id, facility_id, event_type, date, start_at, end_at, demand_json | Event demand add-ons | MVP | Kien | Demand & Event | Hair cutting, CGAT, med checking, training
calendar_days | calendar_day_id, facility_id, date, day_type, holiday_name, is_agency_allowed, agency_cost_multiplier, staff_cost_multiplier, notes | Public holiday, statutory holiday and special-pay day calendar for solver and cost engine | MVP | Kien | Calendar, Cost, Compliance | Required for PH/SH, double-pay, agency allowance and cost multipliers
optimization_jobs | job_id, facility_id, period_id, rule_profile_id, status, plan_mode, solver_limits_json, input_payload_json, result_json, error_json, started_at, completed_at | Async OR-Tools job tracking | MVP | Kien | Roster A/B/C, Solver | Needed because optimization may exceed request timeout
roster_option_scores | score_id, roster_version_id, plan_mode, constraint_score, hard_violation_count, soft_penalty_total, objective_weights_json, infeasible_reasons_json | Persist A/B/C solver scores and reasons | MVP | Kien | Roster A/B/C, KPI | Can be merged into roster_kpi later but explicit table is clearer for MVP
employment_type_values | value, label, description, default_min_rest_minutes, is_external | Standardized employment type lookup | MVP | Kien | Staff, Contract, Solver | Values: local_ft, local_pt, imported_labor, agency, outsource, casual
staff_contract_hour_rules | staff_id, contract_hours_per_week, max_weekly_hours, max_monthly_hours, min_rest_minutes, effective_from, effective_to | Explicit contract hour rules for max-hour constraints | MVP | Kien | Compliance, Solver | Can be implemented by expanding staff_contracts columns

## API Endpoints
Endpoint | Method | Purpose | Request Inputs | Response | Phase | Owner | Notes
/auth/login | POST | User login | email, password | session, role | MVP | Kien | Supabase Auth wrapper optional
/rosters/:period | GET | Get roster by period | facility_id, start/end | roster, shifts, assignments | MVP | Kien | Used by roster calendar
/shifts | POST | Create shift | date, type, time, wing, required role | shift_id | MVP | Kien | Manual creation
/shifts/:id | PATCH | Edit shift | shift fields | updated shift | MVP | Kien | Log manual override if assignment changes
/optimize-roster | POST | Generate roster A/B/C | period, facility_id, constraints profile | job_id or roster options | MVP | Kien | May need async job
/validate-roster | POST | Validate hard constraints | roster_id | violation list | MVP | Kien | OR-Tools/rule engine
/compliance/ratio | GET | Staff-to-resident ratio | facility_id, period, wing | ratio by role/shift | MVP | Kien | Prototype staffing ratio card
/leave-requests | POST | Submit leave request | staff_id, type, dates, reason | request_id | MVP | Kien | Staff app
/sl-incidents | POST | Submit urgent SL/DSL | staff_id, shift_id, type | incident_id | MVP | Kien | ROI A2
/replacement-candidates | GET | Suggest replacement staff | shift_id, role, date | candidate list | MVP | Kien | Rule-based first
/roi/summary | GET | ROI dashboard summary | facility_id, period | A1, A2, agency saving | MVP | Kien | ROI v2.2 formula
/kpi/conflict-rate | GET | Conflict KPI | roster_id or period | conflict rate | MVP/Phase 2 | Kien | From violation_log
/kpi/an-gini | GET | AN fairness KPI | period | gini value | Phase 2 | Kien | Python/Supabase RPC
/pressure/:period | GET | Staffing pressure forecast | period, facility_id | pressure signals | Phase 2 | Kien | Rule scoring first
/workload-pulse | POST | Weekly Workload Pulse input | wing, occupancy, dependency counts | saved record | Phase 2 | Cherry/Gary UI + Kien | RN input form
/reports/generate | POST | Generate PDF/Excel report | type, period, roster_id | file_url | MVP | Kien | React-pdf / xlsx
/resident-counts | POST | Create or update daily resident count by facility/floor/ward/care level | facility_id, date, wing, floor, ward, care_level, resident_count | saved count | MVP | Kien | Used as denominator for staffing ratio
/compliance/minute-ratio | GET | Minute-level staffing ratio calculation | facility_id, date, roster_id | minute-level pass/fail, breach minutes | MVP | Kien | Core Code of Practice compliance logic
/reports/staffing-ratio | POST | Generate staffing ratio report | roster_id, date range, report_type | file_url or report rows | MVP / Phase 2 | Kien | Two report types: per-shift and statutory time-window
/kpi/staffing-ratio-compliance | GET | Staffing ratio compliance KPI | facility_id, period | breach count, breach minutes, pass rate | MVP | Kien | Top-level compliance KPI
/kpi/shift-fairness | GET | Fairness by shift type | facility_id, period, shift_type | gini, variance, distribution | Phase 2 | Kien | Beyond AN Gini
/rule-profiles | GET/POST | List or create facility rule profiles | facility_id, name, template | rule_profile | MVP | Kien | Rule Builder profile CRUD
/rule-profiles/:id/activate | POST | Activate a rule profile for facility | profile_id | active profile | MVP | Kien | Only one active profile per facility unless versioning requires otherwise
/rules | POST | Create Rule Builder rule | rule_type, rule_code, severity, config_json | rule | MVP | Kien | Facility-scoped and versioned
/rules/:id | PATCH | Update/deactivate rule | rule fields, config_json | updated rule | MVP | Kien | Create rule_versions entry
/rules/templates | GET | Get system rule templates | optional facility_type | templates | MVP | Kien | A院舍/B院舍/SWD templates
/rules/:id/test | POST | Test one rule against sample roster | rule_id, roster_id or sample_json | pass/fail, violations | MVP | Kien | Rule Builder acceptance
/compliance/an | GET | AN/sleep/DO/PH compliance | facility_id, period, roster_id | staff-level AN metrics and violations | MVP + Phase 2 | Kien | Supports AN Gini and sequence rules
/optimization-jobs/:id | GET | Get optimization job status/result | job_id | status, progress, roster_options | MVP | Kien | Needed when Roster A/B/C exceeds request timeout
/sl-incidents/:id/resolve | POST | Resolve urgent SL/DSL by assigning candidate | incident_id, candidate_staff_id, decision | updated assignment, future_debt | MVP | Kien | Emergency cover close loop
/kpi/external-workforce | GET | External workforce dependency and cap KPI | facility_id, period | dependency, cap violations, agency cost | MVP | Kien | PT/agency/outsource governance KPI
/future-debt | GET | Future AN/CL/CO/OT debt ledger | facility_id, staff_id, period | debt rows | MVP | Kien | Feeds next-cycle scheduling
/calendar-days | GET/POST | List or create calendar day flags for PH/SH/special-pay days | facility_id, date, day_type, multipliers, agency allowance | calendar day rows | MVP | Kien | Feeds solver cost and agency constraints
/optimize-roster payload contract | SPEC | Stable JSON contract for Python OR-Tools service | facility_id, period_id, rule_profile_id, plan_mode, locked_assignments, approved_leave_request_ids, include/exclude staff, solver_limits, writeback | job_id, roster_options, scores, infeasible_reasons | MVP | Kien | Document in OpenAPI and stable mock JSON
/roster-option-scores/:roster_version_id | GET | Get solver scores and weight breakdown for a roster option | roster_version_id | constraint_score, hard_violation_count, soft_penalty_total, objective_weights_json | MVP | Kien | Can be served through /roster-versions/:id if preferred

## ROI KPI Mapping
ROI/KPI | Formula / Method | Database Tables | Tool | Phase | Owner | Target / Note
A1 Roster Time Saving | (26h - 7h) × HK$409 = HK$7,771/month | facilities, survey_input, roster_kpi | ROI dashboard | MVP | Cherry/Gary UI + Kien API | Baseline configurable
A2 Emergency Cover Saving | SL/DSL incidents × 0.75h × HK$409; March 2026 actual = 46 incidents => HK$14,111/month | sl_incidents | Alert engine + matching | MVP | Kien | Directly supports ROI
Part B Agency Saving | agency_cost × 5%; conservative case = HK$7,404/month based on HK$148,070 actual | agency_assignments, facility_budget | SQL View | MVP | Kien | OT excluded from financial ROI
Conflict Rate | Hard constraint violations ÷ total shift assignments × 100% | violation_log, shift_assignments | OR-Tools + SQL | MVP/Phase 2 | Kien | 6mo target -20%; long-term -41% reference
AN Gini | SUM_i SUM_j ¦xi-xj¦ ÷ (2 × n² × x_mean) | shift_assignments, staff | Python/Supabase RPC | Phase 2 | Kien | Baseline <0.25; long-term <=0.10
Manual Override Rate | manual changes ÷ total assignments | manual_override_log | Dashboard | MVP | Kien | Indicator of AI usability
AI Acceptance Rate | AI assignments retained ÷ total AI assignments | roster_versions, manual_override_log | Dashboard | MVP | Kien | Key pilot adoption KPI
XGBoost R² | Forecast vs actual staffing pressure, target R² >=0.75 long-term | pressure_signal, sl_incidents, roster_kpi, agency_assignments | XGBoost | Phase 3/4 | Kien | Not MVP; dataset too small initially
OT/CL Dashboard | Total OT/CL hours per month by shift type | attendance or manual_ot_entries, roster_kpi | Dashboard only | MVP/Phase 2 | Cherry/Gary UI + Kien API | No financial ROI target
SWD Staffing Ratio Compliance | Pass/fail and breach minutes based on daily resident count and minute-level staff coverage | daily_resident_counts, staffing_ratio_rules, shifts, shift_assignments, staffing_ratio_reports | SQL/Python minute overlap + dashboard | MVP | Kien | Core compliance KPI; must be shown before publish
Per-shift Staffing Ratio Report | Calculate actual staff-to-resident ratio for each actual shift by role and wing/ward | shifts, shift_assignments, daily_resident_counts | Report SQL View | MVP | Kien | Report type 1
Statutory Time-window Ratio Report | Calculate staffing ratio across Code of Practice time windows using minute-level overlap | staffing_ratio_rules, shifts, shift_assignments, daily_resident_counts | Minute overlap engine + report | MVP / Phase 2 | Kien | Report type 2
All Shift-Type Fairness | Gini/variance/count distribution for A, P, N, A/N, weekend, PH, difficult shifts | shift_assignments, staff, shift_fairness_metrics | Python/Supabase RPC | Phase 2 | Kien | Beyond AN Gini
External Workforce Dependency | PT/agency/outsource shifts ÷ total shifts; plus cap violations by role | shift_assignments, agency_assignments, staff, violation_log | SQL View + dashboard | MVP | Kien | Track agency/PT reliance and RCW/HCA cap risk
Task Coverage Accuracy | Qualified task assignments ÷ required task assignments | task_definitions, task_assignments, staff_qualifications, violation_log | Rule engine + SQL | MVP | Kien | Important for A院舍 task-code layer
P-shift Risk Score | Weighted score using P shift shortages, leave count, agency count, occupancy and event flag | pressure_signal, shifts, leave_requests, daily_resident_counts | Rule scoring first | MVP / Phase 2 | Kien | Important for B院舍 P-shift gap risk
Future Debt Balance | Open AN/CL/CO/OT debt by staff and period | future_debt_ledger, shift_assignments | Dashboard | MVP | Kien | Prevents hidden unfairness after emergency cover
Constraint Score | 100 - normalized hard/soft penalty; hard violations should drive score below publish threshold | roster_option_scores, violation_log, roster_kpi | Solver scoring | MVP | Kien | Displayed for each Roster A/B/C option
Hard Violation Count | Count unresolved hard violations by roster version | violation_log, rule_definitions | Compliance KPI | MVP | Kien | Must be zero for normal publish
Soft Penalty Total | Weighted sum of agency, OT, future debt, unmet request and fairness penalties | roster_option_scores, rule_definitions, roster_kpi | OR-Tools objective | MVP | Kien | Explains why A/B/C differ
Request Satisfaction Rate | Approved/fulfilled valid AL/DO/Request Duty ÷ valid requests | leave_requests, shift_assignments | Roster comparison | MVP | Kien | High priority for Staff-Satisfaction version
Future Debt Count | Open future debt entries caused by emergency or optimization decisions | future_debt_ledger | Fairness/operational KPI | MVP | Kien | Should be minimized in balanced plan

## Tools Ownership
Tool | Purpose | Needed for MVP | Owner | Risk | Decision Needed from Kien
Next.js 14 | Frontend, dashboard, staff PWA | Yes | Cherry/Gary + Kien review | UI can be built, but DB/API integration needs Kien | Confirm repo structure and component standards
Tailwind + shadcn/ui | Consistent UI components | Yes | Cherry/Gary | Avoid leaving components on mock data | Confirm reusable component library
Supabase Auth | Login, roles, session | Yes | Kien | Incorrect RLS can cause data leakage | Confirm auth roles and RLS test plan
Supabase PostgreSQL | Core database | Yes | Kien | Poor schema design causes rework | Confirm schema before UI data binding
FastAPI | AI/optimization backend | Yes | Kien | API contract must be clear | Provide OpenAPI spec/mock JSON
OR-Tools CP-SAT | Compliance scheduling hard constraints | Yes | Kien | Infeasible rosters need explanation and fallback | Confirm infeasible handling and fallback strategy
React-pdf | PDF reports | Yes | Cherry/Gary templates, Kien data binding | Chinese font rendering must be tested | Confirm PDF library and font approach
Cloudflare R2 | Store PDFs, certificates, files | Recommended | Kien | Signed URL and permissions required | Confirm if MVP uses R2 or Supabase storage
Redis Upstash | Rule cache / job status | Phase 2 | Kien | Not required for MVP | Confirm if async jobs need Redis in MVP
XGBoost / scikit-learn | Staffing pressure forecast | Phase 2 | Kien | Needs enough historical data | Confirm minimum dataset and target variable
pymoo / DEAP | Pareto / NSGA-II | Phase 3 | Kien | Too complex for MVP | Confirm whether CP-SAT scoring is enough before Pareto
LLM Provider | Explanations, summaries, notifications | Optional MVP | Kien | Do not depend only on Claude in Hong Kong | Confirm provider abstraction for OpenAI/Gemini/Claude/fallback
MLflow | Model versioning | Phase 3/4 | Kien | Too much overhead early | Use model_run_log first?
Supabase migrations | Versioned SQL schema and rollback path | Yes | Kien | Schema drift can break frontend/API | Confirm migration naming and deployment process
Rule-only fallback mode | Allow compliance validation and manual roster use if LLM/optimizer fails | Yes | Kien | Pilot must not depend on LLM or optimizer uptime | Confirm fallback user flow
OpenAPI / stable mock JSON | Frontend/backend contract before DB binding | Yes | Kien | Prototype/DB mismatch | Publish mock JSON for key endpoints
Supabase Storage | Store reports/certificates before R2 decision | Recommended MVP | Kien | Storage permissions and signed URL needed | Confirm storage choice vs Cloudflare R2
FastAPI OR-Tools JSON contract | Stable API boundary between Next.js/Supabase and Python solver | Yes | Kien | Without payload contract FE/BE integration will rework | Define OpenAPI schema and mock JSON before solver implementation
optimization_jobs table | Async job status for Roster A/B/C solver runs | Yes | Kien | Web request timeout if solver runs synchronously | Implement polling via /optimization-jobs/:id
calendar_days seed source | Public holiday/statutory/special-pay day data for Hong Kong and facility-specific rules | Yes | Kien + Product | Wrong PH/SH data affects agency/cost decisions | Confirm seed source and manual override UI
OR-Tools hard constraint tests | Unit/fixture tests for each hard constraint | Yes | Kien | Illegal rosters may pass validation | Build fixtures for SWD ratio, max hours, rest, leave and task eligibility

## Risk Register
Risk | Possible Issue | Recommended Solution | Rescue Time Estimate | Owner | Phase
CP-SAT infeasible | H1-H13 too strict or missing data prevents roster generation | Return infeasible reason; provide Plan B/C soft fallback | 1–2 days; severe 3–5 days | Kien | MVP
RLS misconfiguration | Facility A can see Facility B data | Add facility_id to all tables; write RLS tests | 1–2 days | Kien | MVP
Roster A/B/C too slow | Three async jobs exceed 60 seconds | Background jobs + job status polling + cache | 2–4 days | Kien | MVP
ROI numbers inaccurate | agency/SL/OT sources inconsistent | Define data source clearly and show assumptions in dashboard | 1–2 days | Kien | MVP
Manual override not tracked | Cannot calculate AI acceptance | Log every assignment edit | 1 day | Kien | MVP
Chinese PDF broken | React-pdf font issue | Use Noto Sans CJK and server-side rendering | 1–2 days | Kien | MVP
LLM API unstable | Provider downtime or region limitation | Provider abstraction; fallback to rule-only mode | 2–3 days | Kien | MVP/Phase 2
Prototype cannot connect to real DB | Mock data differs from DB schema | Define API contract before UI implementation | 2–5 days | Kien + Cherry/Gary | MVP
Rule Builder misconfiguration | Manager creates conflicting or invalid rule config | Rule test endpoint, templates, validation and version rollback | 1–3 days | Kien | MVP
Facility profile drift | A/B facility rules in DB diverge from agreed workflow | Seed scripts, rule profile versioning and product sign-off | 1–2 days | Kien + Cherry/Gary | MVP
External workforce cap false positive | PT/agency cap calculated against wrong denominator | Define full-time equivalent denominator and store source rows | 1–2 days | Kien | MVP
Future debt not carried forward | Emergency replacement creates unfairness in next roster cycle | future_debt_ledger must be solver input | 1–2 days | Kien | MVP
Rule-only fallback missing | System unusable if optimizer/LLM fails | Manual CRUD + deterministic validation must remain available | 1–2 days | Kien | MVP
Missing public holiday calendar | Solver does not know PH/SH/special double-pay days and may schedule agency incorrectly | Add calendar_days table, seed HK/facility holidays, allow manual override | 1–2 days | Kien + Product | MVP
Vague optimizer payload | Frontend, Supabase and Python solver use different field names and data shape | Define OpenAPI payload/response and stable mock JSON before implementation | 1–2 days | Kien | MVP
Hard constraints implemented as soft warnings | Roster may violate SWD ratio, rest or max-hour rules | Explicit OR-Tools hard constraint mapping and fixtures | 2–4 days | Kien | MVP
A/B/C weights inconsistent | Different developers interpret roster options differently | Store objective weight presets and plan_mode in DB/config | 1–2 days | Kien + Product | MVP
Solver output not persisted | Frontend cannot compare/publish generated options after job finishes | Write solver result to roster_versions, shift_assignments, roster_option_scores and roster_kpi | 1–2 days | Kien | MVP

## Manus Sync Summary
Updated At | Updated By | Summary
2026-05-30 | Manus AI | Aligned workbook with Kien backend/database/rule-builder MVP spec; appended missing tasks, DB schema rows, API endpoints, KPI items, tool decisions and risk register entries.
2026-05-30 | Manus AI | Added Edge Cases & Data Structures sync: calendar_days/public holidays, OR-Tools hard constraint mapping, Roster A/B/C weight presets, optimizer payload contract and solver writeback/scoring.

## Solver Contract
Section | Key | Value
Hard Constraint | one_staff_no_overlap | Forbid overlapping assignments for same staff: x[s,a] + x[s,b] <= 1 when intervals overlap.
Hard Constraint | approved_leave_unavailable | If approved leave covers shift time, x[s,shift] = 0.
Hard Constraint | required_coverage | sum(x[s,shift] for eligible staff in role/unit) >= required_count[shift,role,unit].
Hard Constraint | swd_ratio | actual_count[role,unit,time_window] >= ceil(resident_count / ratio).
Hard Constraint | min_rest | For shifts too close under staff min_rest_minutes, x[s,a] + x[s,b] <= 1. Imported labor default 720 minutes.
Hard Constraint | max_hours | sum(duration_minutes[shift] * x[s,shift]) <= max_minutes[s,period].
Hard Constraint | task_eligibility | Staff without required audit/skill cannot be assigned restricted task.
Plan Weight | A Cost-Optimized | Agency=100, OT=90, future_debt=80, unmet_request=25, fairness=40.
Plan Weight | B Staff-Satisfaction | Agency=30, OT=40, future_debt=40, unmet_request=100, fairness=85.
Plan Weight | C Balanced | Agency=60, OT=65, future_debt=60, unmet_request=65, fairness=70.
Payload Request | POST /optimize-roster | facility_id, period_id, rule_profile_id, plan_mode, locked_assignments, approved_leave_request_ids, include_staff_ids, exclude_staff_ids, solver_limits, writeback.
Payload Response | roster_options | job_id, status, roster_version_id, version_label, plan_mode, constraint_score, hard_violation_count, soft_penalty_total, kpi, infeasible_reasons.
Writeback | tables | roster_versions, shifts, shift_assignments, violation_log, roster_kpi, roster_option_scores.